**SAMPLE PLANNING CALENDAR FOR MAY DAY STRONG EVENTS**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Monday** | **Tuesday** | **Wednesday** | **Thursday** | **Friday** | **Saturday** |
| April 14Form a planning committee and schedule your first meeting. | April 15Map out your promotion plan, including who are your target audiences.  | April 16Create dream list of speakers and begin outreach. Contact local unions, businesses, non-profits, and other groups who may be interested in partnering with you on this event. | April 17Planning committee decides event date, time, and location.Check with officials to determine if you need a permit. | April 18Decide how you are tracking registration and collecting attendee contact information. | April 19Start promotion to potential attendees.Outreach to community, fellow union members, and parents to participate. |
| April 21Identify volunteers to help with set up/clean up and other in-person roles for your 3event. | April 22Secure a working list of available and interested speakers and begin to create the event run-of-show.  | April 23Draft your media plan and begin outreach to reporters by sending out your media advisory. | April 24Send reminder calls, emails & texts to registrants and potential participants. | April 25Finalize and prep speakers.ID photographers and social media point people for event coverage. | April 26Canvass the neighborhood to drive turnout, increase interest and secure commitments. |
| April 28Do a run-through of the logistics for the event with your planning team. | April 29Submit updates on planned event to NEA at action@nea.org.Pitch media. |  April 30Reminder calls, emails, texts to build turnout.Pitch media. | May 1Host your event! Remember to work with the press and your communications team to cover the event publically.  | May 2Continue to tell your story online and to the media.Share photos, media and highlights w/ NEA at action@nea.org. | May 3Thank supporters and tell them to stay tuned.Meet with your planning team to debrief and decide on next steps for your movement! |